

Event Planning and Procedures Handbook

Creating Supporting Documentation for Events

****

Updated July 2023

Contents

[1. Planning and Procedure Handbook 4](#_Toc97199264)

[1.1. Overview 4](#_Toc97199265)

[1.2. How to use this handbook 4](#_Toc97199266)

[1.3. Accountability 5](#_Toc97199267)

[1.4. Event Definitions 5](#_Toc97199268)

[2. The Event Plan 6](#_Toc97199269)

[2.1. Section 1 Outline – The Event Detail 6](#_Toc97199270)

[2.2. Section 2 Outline – Risk Management Plan 6](#_Toc97199271)

[3. Section 1 – The Event Detail 7](#_Toc97199272)

[3.1. Event Title, Dates and Duration 7](#_Toc97199273)

[3.2. Location and Accessibility 7](#_Toc97199274)

[3.3. Acknowledgement of Traditional Land Owners and Welcome to Country 8](#_Toc97199275)

[3.4. Program Overview: Aims, Objectives, Purpose and Audience 9](#_Toc97199276)

[3.5. Event Program/Running Sheet 9](#_Toc97199277)

[3.6. Timelines 9](#_Toc97199278)

[3.7. Key Stakeholders 11](#_Toc97199279)

[3.8. Councillor Involvement 11](#_Toc97199280)

[3.9. Contractors 12](#_Toc97199281)

[3.10. Provision of Food 12](#_Toc97199282)

[3.10.1. FoodTrader 12](#_Toc97199283)

[3.10.2. Community Health Services Contact Details 13](#_Toc97199284)

[3.10.3. Information 13](#_Toc97199285)

[3.11. Safe Amusement Rides 13](#_Toc97199286)

[3.11.1. Hazards 13](#_Toc97199287)

[3.11.2. Risk Controls 13](#_Toc97199288)

[3.11.3. Inflatable Rides 14](#_Toc97199289)

[3.12. Insurance 14](#_Toc97199290)

[3.13. Budget 15](#_Toc97199291)

[3.14. Layout & Site Map 15](#_Toc97199292)

[3.15. Toilets 16](#_Toc97199293)

[3.16. Waste 17](#_Toc97199294)

[3.16.1. Waste Generation and Disposal 17](#_Toc97199295)

[3.16.2. Waste Hierarchy 18](#_Toc97199296)

[3.16.3. Minimising Waste 18](#_Toc97199297)

[3.16.4. Reducing Litter 18](#_Toc97199298)

[3.16.5. Waste Infrastructure 19](#_Toc97199299)

[3.17. Water 20](#_Toc97199300)

[3.18. Power 21](#_Toc97199301)

[3.19. Event Noise/Music 22](#_Toc97199302)

[3.20. Signage 22](#_Toc97199303)

[3.21. Smoking Laws 23](#_Toc97199304)

[3.22. Transport, Parking, & Pedestrian Management 24](#_Toc97199305)

[3.23. First Aid 26](#_Toc97199306)

[3.24. Security and Crowd Control 27](#_Toc97199307)

[3.25. Weather 27](#_Toc97199308)

[3.26. Permits 28](#_Toc97199309)

[3.26.1. Liquor Licence 28](#_Toc97199310)

[3.26.2. Provision of Food and/or Temporary Food Event Permit 30](#_Toc97199311)

[3.26.3. APRA & PPCA Event Licence 30](#_Toc97199312)

[3.26.4. Roadside Promotional Boards Permit 30](#_Toc97199313)

[3.26.5. Temporary Banning of Dogs, Alcohol and other items 31](#_Toc97199314)

[3.26.6. Fireworks/Pyrotechnics Displays 31](#_Toc97199315)

[3.26.7. Road and Footpath Closure Permits 31](#_Toc97199316)

[3.26.8. Infrastructure and Temporary Structures 32](#_Toc97199317)

[3.27. COVIDSafe Events - Victorian Government Requirements 33](#_Toc97199318)

[3.28. Event Planning Template 33](#_Toc97199319)

[4. RISK MANAGEMENT PLAN AND EMERGENCY RESPONSE PLAN 37](#_Toc97199320)

[4.1. Risk Management Plan 37](#_Toc97199321)

[4.2. What is Risk? 37](#_Toc97199322)

[4.3. What is Risk Management? 37](#_Toc97199323)

[4.4. Risk Management Process 37](#_Toc97199324)

[4.5. How to Conduct a Risk Assessment 38](#_Toc97199325)

[4.5.1. Risk Analysis - Step 1 Consequences 38](#_Toc97199326)

[4.5.2. Risk Analysis - Step 2 Likelihood 39](#_Toc97199327)

[4.5.3. Risk Analysis - Step 3 Risk Matrix 39](#_Toc97199328)

[4.5.4. Risk Examples 40](#_Toc97199329)

[4.6. Emergency Response Plan 42](#_Toc97199330)

# Planning and Procedure Handbook

## Overview

Maroondah City Council plans, manages and supports a range of festivals, functions and events held in Council facilities and on Council owned land. This handbook provides a guideline for event organisers to maintain a safe, successful and well-documented event.

There are several stages that event organisers must agree to undertake during the planning and development stages to gain approval for use of Council land.

These are:

Stage 1: Submit the online Event Application Form found here [Event Application Form](http://feedback.maroondah.vic.gov.au/FS/fs-EventApplication.aspx)

Stage 2: Council will review the Event Application Form, assess the risk level and respond with a letter of in principle support and conditions, including if there is a need for an Event Plan, or rationale for non-approval of the event

Stage 3: Submit signed letter of conditions and all supporting material, including Event Plan if required, to Council as outlined in the written response from Council

Stage 4: Council to review Event documentation and final approval for use of Council land is given

Stage 5: Deliver Event

Stage 6: Complete Event Evaluation

|  |  |
| --- | --- |
| **Risk Level**  | **Event includes**  |
| Low Risk  | Small event up to 50 people with minimal infrastructure, no impact on traffic conditions or extensive activities – no event plan required |
| Medium Risk  | Attendance is over 50 people, may impact on traffic conditions, medium noise impact, food and beverage trading, amusements, performers - event plan required |
| High Risk | Over 2500 participants, substantial infrastructure required, fireworks\ pyrotechnics, high noise impact, road closures, event does not meet Council policies, insufficient time to prepare or Council deemed activities to be unsafe |

## How to use this handbook

This handbook has been designed to detail elements of an event you will need to consider throughout the planning process. It has been divided into sections for ease of reference. At the end of each section you will find a summary of the key items for consideration.

If you have been advised by Council that you are required to complete an Event Plan, Council will advise which sections of the handbook you need to include as part of your final document. Your Event Plan should be set up under the same headings within the handbook. It is strongly recommended that you cross check the information included in your Event Plan against our template which you will find in section 3.26.

If you need any assistance during the process, please contact Council’s Community Events Officer on 9294 5722.

## Accountability

This handbook is to be used as a reference document. Event organisers should refer to this document for information on Council’s requirements and organisers responsibilities.

The handbook should be the first place users look to for information relevant to hosting an event on Council land. It gives users a starting point to address any issues in developing an event plan.

The event plan will be your operational document that provides an overview of all the elements that you need to consider throughout the entire event process.

Once completed Event Plans are to be submitted to Councils Community Events Officer. If your event becomes an annual event your plan can be updated and used for future events.

## Event Definitions

**Event: -** Any planned activity or function that requires specific planning where people congregate for a unique purpose. The purpose may include but not limited to community, cultural and environmental gatherings, commercial activities, celebrations and some sporting events such as a fun run or major football and cricket final.

**Council Land: -** Council land may include but not limited to buildings, sporting reserves, open space, roads and car parks that are owned, managed and maintained by Maroondah City Council.

**Event Organiser/Co-ordinator: -** The individual or organisation that is responsible for planning, implementing and managing all aspects of the event.

**Event Plan: -** A compulsory document that must be provided by the Event Organiser of medium/high risk events. The Plan should detail the planning elements of an event and incorporate all key stakeholders and aspects of the event being organised.

**Bump In: -** The timing at which site preparation works are taking place, including the setup of the temporary structures.

**Bump Out: -** The timing at which the participation aspect has been completed and temporary structures are removed and pack up occurs.

**Accessible Event: -** Maintaining an event where people of all abilities can participate in the event without any limitations.

**Access Guide: -** An Access Guide is a promotional document developed for an event that incorporates a site map, key access points, pathways and facilities such as accessible toilets and parking for people with a disability.

**Temporary Structures: -** Temporary structural items that are brought in specifically for the event. They may include, but are not limited to marquees or tents, stages or platforms or seating stands.

# The Event Plan

## Section 1 Outline – The Event Detail

The Event Plan includes two main sections, the Event Detail and the Risk Management Plan. The Event Detail will include all event management information that is listed in the check list below and detailed in the following pages. This will assist you to create your key document throughout the entire event process and act as a planning tool, a working document and a constant point of reference.

|  |  |  |
| --- | --- | --- |
| * Event Title, dates, duration
* Location including accessibility
* Program Overview – aims, objectives/purpose and audience
* Timetable/running sheet
* Event Timelines
* Key Stakeholders including Councillor involvement
* Contractors – caterers, rides etc
* Budget
* Layout & site map including additional infrastructure
* Toilets – including accessibility
* Water
* Power
* Signage
* Traffic Management -transport and car parking
 |  | * Insurance
* Security
* Weather
* Permits (if applicable)
* Liquor License Permit
* Provision of Food and/or Temporary Food Event Permit
* APRA & PPCA Permits
* Roadside Promotional Boards Permit
* Temporary Banning of Dogs, Alcohol and other items
* Fireworks\Pyrotechnics Displays
 |

If your event includes any of the items listed below and they were not detailed within your initial online event form (step 2 above) please contact the Community Events Officer on 9294 5722 prior to the completion of your Event Plan:

* More than 500 people
* Camping
* Councillors/Mayor involvement
* Fireworks or Pyrotechnics Displays
* Sale of goods and merchandise
* Ticket sales
* Road or Street Closures

## Section 2 Outline – Risk Management Plan

The Risk Management Plan will detail all associated risks that may impact on your event including the Emergency Response Plan (see section 4 for details).

***The Risk Management Plan needs to be viewed by Council’s Community Events Officer prior to your event as we want to ensure your event is a huge success.***

# Section 1 – The Event Detail

## Event Title, Dates and Duration

To start your Event Plan, you must list the key information about your event. This includes the event name, the date or dates that it will be held on, the duration of the event and the location.

## Location and Accessibility

A venue needs to be sourced that is suitable for the size of the event, taking into consideration the program and the number of people you are expecting to attend. All Council owned indoor venues will have a maximum capacity, hours of operation, noise level, catering and alcohol requirements that must be adhered to.

It is also important that you take into consideration your surrounding environment and the impact it may have on residents, local businesses and other activities or user groups within the area. Approximately 2 weeks out from the event conduct a letter drop to residents and business that advises them of your event and warns of any possible noise implications. As a minimum ensure that the delivery captures all residents that will be directed impacted by noise and/ or traffic implications.

If you are holding an event within Council’s parks and reserves, you must protect all park facilities from damage and avoid inappropriate use.

Key areas to protect are:

* Surface (the grass) – ensure there is no infrastructure on site that may burn the grass during hot weather and ensure vehicles or machinery do not cause rutting or indentations in the grass
* Trees – do not hang infrastructure from branches and no vehicles are to be under the reach or canopy of any tree
* Vegetation – ensure there are adequate pathways for the number of guests so there is no cutting across greenery or damage to vegetation on garden beds
* Furniture – ensure no graffiti or damage occurs
* Fencing - do not attach any items to fencing
* Wildlife – ensure all remaining food is taken with you and not left behind
* Water Features and Water Bodies – ensure adequate safety measures are in place when near these features

A post event inspection will be undertaken to ensure the venue/site is left in reasonable condition. Should any damage occur the Event Organiser will be responsible for the costs associated in rectification works.

The selection of your venue/site should also be based around the requirements of your event. The less temporary infrastructure required for your event such as stages, marquees, audio/visual equipment, power and toilets the easier your event will be to organise. Also think about accessibility and how your event will be accessible for all the community. You must make sure there is ample parking, including accessible parking. If your venue does not provide the necessary parking requirements, then you may have to source appropriate car parking off site and prepare a Traffic Management Plan (TMP).

The following is a list of recommendations that will assist you in making your event accessible for all. This list is certainly not exhaustive; consider additional recommendations that are specific to your event.

* Continuous accessible path – consider width and surface material
* Temporary portable ramps
* Viewing sections at stage/attraction areas with accessible pathways to the site
* Clear signage with large font, contrasting colours and tactile indicators
* Accessible toilets and pathways to them
* Accessible parking – they should be in close proximity as possible to the entrance point of the event. Consider access to pathways from the carpark.
* A venue that provides wide self-opening or easy to open doors
* Acceptance of Companion Cards for entry fee events
* Recharge stations for electric wheelchairs and mobility units
* Accessible (mobility) utilities such as drinking fountains, picnic tables/seating and bins
* Appropriate handrails and contrasting line marking on steps, ramps etc.
* Use of international symbols
* Marketing and event promotion to be clear, large and contrasting font. Use Arial font size 18 on printed material
* Provide a site map clearly showing access for all facilities
* Brief staff on the location of accessible facilities
* Brief key staff (Wardens) of emergency response procedures taking into consideration people who may require assistance during an evacuation.

***In this section of your event plan list what facilities are available that are accessible and how you intend to make sure that your event program can be accessed by your intended audience.***

## Acknowledgement of Traditional Land Owners and Welcome to Country

Maroondah City Council reaffirms its commitment to maintaining a culturally diverse, tolerant and open society, united by an overriding commitment to our Nation. The Maroondah community and Council clearly recognise the need to acknowledge the contributions of Indigenous Australians of both our past and future. Accordingly, Maroondah actively encourages opportunities that support recognition of Indigenous Australians by acknowledging the strength of their culture and its importance to our history, our National pride and our future development.

**The following is a suggested Acknowledgement of Country to be used in opening speeches and welcomes:**

**<Insert Organisation Name**>*, in the spirit of Reconciliation, acknowledges the Wurundjeri People of the Kulin Nation as traditional custodians* *of the land on which we are gathered today, where Indigenous Australians have performed age-old ceremonies. We pay our respects to their Elders, past, present and emerging.*

## Program Overview: Aims, Objectives, Purpose and Audience

The aims and objectives of your event will provide the key directional outcomes for the event and organiser to achieve. They may include the programming purpose of your event and the social, financial, accessible, environmental and promotional outcomes that you aim to achieve. Detail who your event is for and your intended audience.

***In this section of your event plan clearly state in point form the aims and objectives, purpose and audience of your event.***

## Event Program/Running Sheet

The program of your event will be what attracts your audience. If your event has a specific target audience such as young people, business people or families, your program should replicate their interests. Research should be undertaken to make sure the program is of interest.

Document all dealings with external stakeholders whether it be a performer, guest speaker, MC, band etc. You need to be specific on time, duration, location and your expectation for their involvement and fee (if applicable).

Once your program is set and all parties have confirmed their attendance and involvement prepare a running sheet of your event documenting who, where, when, logistics required and person responsible for greeting, understanding any limitations you may have.

***In this section of your event plan keep a copy of the contact list of all people involved in the programming of your event and an up to date running sheet of your program.***

## Timelines

Depending on the scale of the event, planning might occur from 2 months to 6 months out from the event date. Detailed below is a guideline on various aspects of an event. Each event’s timelines will be different and will have differing requirements you will need to fulfil. It is strongly recommended once you have determined your event date work backwards, detailing the tasks required. This will generally determine if you have enough time and resources to undertake a safe and successful event.

Four to six months out from event

* Read Events Held On Council Land Policy
* Find a suitable venue for your event, check the availability with Council
* Submit Online Event Form (at least 6 months prior for annual, or events that include road closures, fireworks, other regulatory permits and/or temporary changes to Local Laws and three months for casual events)
* Receive Council in principle support and conditions letter.
* Develop concept for your event and brainstorm ideas for the program.
* Develop a draft event budget including a fee schedule if sites/promotional opportunities are part of your event.
* Develop sponsorship proposals and seek sponsorship for your event. All sponsors should form part of a sponsorship agreement clearly stating what you will provide in support of their sponsorship. For Council managed events please refer to the Maroondah City Council Sponsorship Policy available from the Community Events Officer.
* If you are seeking community, business or presenter involvement in your event, commence seeking interest.
* Establish what permits are required and documentation needed to support this process.
* Begin your Risk Management Plan

Three months out from event

* Develop a Marketing Strategy.
* Speak to the Council Community Events Officer if you wish to invite Councillors to your event.
* Establish potential logistic and production requirements and acquire quotes.
* If you are seeking community, business or presenter involvement in your event, continue to seek interest.
* Draft concepts for promotional material.
* Develop the Safety Management Plan and Emergency Response Plan for your event.
* Develop Traffic Management Plan

Two months out from the event

* Organise event staff and volunteers (create position descriptions)
* Meet with Emergency Services (if applicable).
* Finalise all permit requirements with Council’s Local Laws and Engineering Departments.
* Finalise program.
* If you are holding your event on Council’s reserves or open space please contact the Community Events Officer to discuss requirements
* Organise catering requirements or confirm food vendors.
* Confirmation of all logistical and production requirements and organisations providing this support.
* Write up your Event Plan.
* Submit Event Plan to Council
* Send out information packs to presenters, performers, organisations and logistical support services documenting date, time, location (include a site/venue map) and a final confirmation of their involvement.
* Finalise all involvement from external sources.
* Finalise layout of your event and final confirmation of all logistical support and production requirements.
* Conduct Risk Management Plan specific to the venue/site.
* Conduct a letter drop in the immediate area to advise potential guests and warn of potential noise
* Add event to “what’s on Maroondah”

<http://directories.maroondah.vic.gov.au/CA256E7F0018F79E/vwNavigator?OpenForm>

One month out from the event

One week out from the event

* Undertake a site meeting.
* Staff briefing on all facets of the event including safety systems in place and location of first aid and Emergency Services (if required).
* Oversee or confirm the site layout.

Day prior to the event

* Greeting and inducting staff to the site.
* Co-ordination of staff.
* Confirmation that all logistical requirements and temporary structures are in place.
* Final check on facilities – toilets, water etc to see if they are usable and functioning.
* Final Hazard and Risk Inspection (major event will require each area to undertake this).
* Opportunity to take photos of pre event site

Event Day

* Ensure all staff, volunteers and contractors arrive as per agreements.
* Ensure all safety measures are in place.
* Run Event.
* Ensure the event site is cleaned up with all rubbish removed.

After the event

* Evaluate the event. Include feedback from staff, participants/presenters, visitors and venue/site (if applicable).
* Send out thank you letters to all involved in the event.
* Follow up invoices and finalise budget.
* Make sure all areas of the event are documented and retained for future reference.
* Council to conduct post event site inspection for damage

***In this section of your Event Plan, clearly document key planning stages of your event, the timeframe, who is responsible for undertaking the task and a section for noting when it has been completed.***

## Key Stakeholders

Key stakeholders are the main contacts you require to run your event successfully. They may include sponsors, performers, staff, key promotional sources, organising committee, logistical companies, emergency management providers such as the Police and Council contacts.

When identifying staff, volunteers and an organising committee it is important to designate set tasks, so everyone is clear on their own role.

***In this section of your event plan list all the key stakeholders including Councillors (if applicable) involved in the event. Provide current contact details such as business hours and mobile contacts, postal address and email address. To make this a practical resource, group the contacts under headings such as sponsors, logistics, Council contacts and so on.***

## Councillor Involvement

Events provide a good opportunity for the Mayor and Councillors to participate whether it is attending or speaking on behalf of Maroondah City Council. If you are interested in having the Mayor and Councillors attend your event, please contact the Councillor Support Officer on 9298 4462.

***In this section provide confirmation from the Councillor Support Officer.***

## Contractors

Most event organisers will engage external service providers at some stage of the event planning phase. This may include but is not limited to any of the following:

* Event Management Companies
* Event Safety Management Companies
* Performers/bands/entertainers/MC’s
* Equipment suppliers – display boards, tables, trestles and business stands
* Temporary infrastructure – toilets, marquees and stages
* Security
* First Aid
* Staff
* Amusement rides

When entering into a contract, you want to make sure you are getting what you need and what you are paying for. It is highly desirable that all contracts be in writing in the form of a letter supported by written agreement to document exactly what you want and are paying for. This also avoids misunderstandings and minimises disagreements over what has been agreed.

On occasion service providers sub-contract their services to another party. If you are happy for a service provider to sub contract the services that you have requested, then you need to make sure you have a copy of the relevant documentation such as insurances and licenses. Whether it is a direct service provider or a sub-contracted provider, you should demand the same level of skill, experience and documentation.

***In this section of your Event Plan please record all the contracts and agreements and supporting documentation required to oversee these contracts.***

## Provision of Food

### FoodTrader

Any event that sells food must have a registration under the Food Act 1984 with Council.

FoodTrader is the new online registration and notification system for temporary and mobile food businesses.

You must use FoodTrader if you:

* sell food or drinks to the public at a stall, or from a trailer or van
* hold a public barbeque
* own a vending machine
* own a water transport vehicle

You **do not** need to register if you are only asking for a voluntary donation or providing for free.

Access FoodTrader to register a temporary food premises or submit a Statement of Trade (SOT) by visiting <https://foodtrader.health.vic.gov.au>

If you need help, please contact Council’s Community Health Services.

### Community Health Services Contact Details

Community Health Services - (03) 9294 5603 or email communityhealth.customerservice@maroondah.vic,gov.au

Maroondah City Council - 1800 88 22 33 or email

maroondah@maroondah.vic.gov.au

### Information

You can complete a free online education seminar called Do Food Safely at <http://dofoodsafely.health.vic.gov.au/>

Food Handler Talks can also be presented by Council’s Community Health Services. For a fee you can be a part of the interactive Food Handler Talk where you can learn about food safety and your responsibilities. Please contact Council’s Community Health Services if you wish to arrange this information session.

Visit Department of Health (DOH) website at <http://www.health.vic.gov.au/>foodsafety for more information on food safety, legislative requirements and education programs.

## Safe Amusement Rides

If you are considering organising amusement rides as part of your event program, then you need to first gain Council approval before confirming the booking. If approved, consider the associated risks and ensure that adequate controls are in place to provide safe amusement rides. Using experienced and accredited suppliers is essential when booking amusement rides or inflatables.

### Hazards

Specific hazards may include:

* Clearance between rides, fixed structures and vegetation;
* Stability of the ride – firmness and slope of the ground and adequate blocking of the ride need to be considered
* Identification of poor maintenance;
* Poor training and operational procedures;
* Inadequate set-up;
* Missing labels or warning signs; and
* Inadequate or inappropriate location of fencing or barricades.

### Risk Controls

While the formal approach to controlling risk involves applying the hierarchy of controls, some standard controls normally considered include:

* Ensuring the ride has been maintained and set-up in accordance with the manufacturer’s instructions;
* Check areas not readily visible to ensure proper maintenance has been undertaken;
* Issues identified in the engineering assessment have been addressed; and
* All operators and supervisors have been trained and attendance has been planned to ensure that adequate levels are available at all times.

*(Excerpt taken from WorkSafe; ‘Advice For Managing Major Events Safely’ 1st edition, April 2006)*

### Inflatable Rides

Specifically related to inflatable amusement rides the following are requirements:

* Ensure that written hire agreements are completed.
* Request evidence from the hirer/operator that the Operator has current public liability cover, preferably $20mil+.
* Request evidence from the hirer/operator that the inflatable amusement ride meets current Australian Standards and is operated in accordance with AS 3533.4.1.
* An experienced/trained operator to supervise the jumping castle for the total period of hire.
* Ensure that the operator provides written instructions in relation to the following control and supervision issues:
* Environmental conditions that may impact patrons use of the device
* The maximum safe wind speed when the device is in use
* The maximum number of patrons that can use the device at one time based on their height, weight or age
* The maximum height, weight or age limits that apply for patrons to use the device
* Patron dress code, including foot wear
* The minimum number of operators/attendants required to supervise the device and any age restrictions that apply.
* Throughout the period of hire, routine inspections should be carried out and recorded by a competent person (+18 years) to ensure that the device continues to be suitable for use. Such inspections should include but not limited to checks of anchors and ropes, that the fabric of the device does not contain any holes or tears, that the air pressure is sufficient for the walls of the device to remain firm and upright.
* A competent person should ensure that any maintenance required, as determined through routine inspections, is performed, for example, removal of debris, securing of anchors and ropes. This information should also be recorded.

***Make sure all hazards and risks are identified in your Risk Management Plan and that adequate measures are documented and acted on.*** ***Please refer to section 4, Risk Management page 37.***

## Insurance

Every event service provider must have appropriate Public Liability Insurance to ensure that you are financially protected and there is protection against loss should an incident occur. Public Liability Insurance is a critical part of responsible management of an event and is an important part of managing risk.

An event organiser should only use companies that have appropriate and current insurance.

The Certificate of Currency must outline:

* The name of the insured
* The limit of the indemnity for any single claim (not less than $20 million)
* Location of coverage
* The policy must be current at the time of the event
* The business activity shown on the Certificate of Currency must be appropriate for the service being provided at the event.

In the lead up to the event it is required that you contact your insurance provider to ensure that events and all activities run throughout your event are specifically covered within your insurance agreement. The policy must be valid over the set-up, event and pack down periods.

***In this section of your Event Plan you should keep an accurate and up to date table of all relevant insurance details of the service providers you are using. You should also keep a copy of the Certificate of Currency of the relevant providers.***

## Budget

Developing a budget for your event is an essential part in effective event planning. Your budget may be set in terms of an allocation of funds however there are other initiatives you can undertake to increase the overall event budget. An event budget relying on a source of income will need to be regularly monitored and updated, as it may affect expenditure. Plan for the unexpected and provide a 10-15% contingency plan. Your budget may include the following:

|  |  |  |
| --- | --- | --- |
| **Expenditure*** Permit fees
* Equipment Hire (toilets, bins, marquees, trestles etc)
* Power (consumption at site/venue, generator hire)
* Venue/Site hire
* PA/production
 | * Marketing/Promotion
* Administration
* Catering
* Entertainers/Performers
* First Aid
* Staff
 | **Income*** Sponsorship
* Site fees
* Entrance fees
* Grants
* Donations
 |

***In this section of your event plan attach a copy of your draft budget.***

## Layout & Site Map

Whether you are running an indoor or outdoor event, a detailed site plan must be supplied. You may find that a number of maps are required such as a general information map, access map and evacuation/emergency map. The following is a suggested list of items that should be clearly located on the map. The items underlined are essential for all events and must be included:

|  |  |
| --- | --- |
| * Proposed road closures (outdoor)
* Parking
* Accessible parking
* Emergency access route (outdoor)
* Vehicle access routes
* Entrances & exits
* Accessible pathways
* First Aid locations
* Toilets
* Accessible toilets
* Power
 | * Lighting
* Stalls - food, businesses, crafts etc
* Staging - main performance areas
* Location of litter bins
* Information stand
* Drinking water taps
* Liquor licensed areas (if applicable)
* Fire extinguisher equipment
* Lost children (if applicable)
* Event amusements & attractions
* Placement of rubbish and recycling bins
 |

When deciding upon layout, think about how different areas and attractions will complement each other. The layout of your event whether it is indoor or outdoor can provide a different experience for your audience. The following is a list of suggestions to consider when deciding your layout:

* Food areas should be in sections where people can make the most of the entertainment/program.
* Toilets, water and First Aid should be located in prominent and accessible locations.
* Accessible parking needs to be clearly marked and managed during the event. Accessible pathways need to link the parking area to the event site.
* Allow space in your layout for people to congregate. You do not want to create areas where there is risk to the audience due to overcrowding.
* If you are organising an outdoor event, consider the use of natural shade and plan your activities in those locations so that the audience can participate in a safe environment.
* If you are using equipment that requires power, locate them close to the power source whether it be mains power or through a generator. You need to manage the risk of power cords in areas where the public can access and walk.

***In this section of your event plan, include a copy of any of the site maps you will be using for your event.***

## Toilets

It is important to ensure that an event has an adequate number of toilet facilities. Cleaning and maintenance of the facilities is extremely important and can often be a determining factor of whether or not attendees enjoy the event. The number of toilets required at your event will depend on several factors including:

* Anticipated crowd numbers
* The gender of patrons (women require more facilities than men)
* The duration of the event or festival
* If alcohol will be available
* Provisions for people with disabilities
* Provisions for parents

Toilet facilities requirements for events without alcohol

|  |  |  |
| --- | --- | --- |
|  | Males | Females |
| Patrons | Toilet | Urinals | HandBasins | Toilet | HandBasins |
| <500 | 1 | 2 | 2 | 6 | 2 |
| <1000 | 2 | 4 | 4 | 9 | 4 |
| <2000 | 4 | 8 | 6 | 12 | 6 |
| <3000 | 6 | 15 | 10 | 18 | 10 |
| <5000 | 8 | 25 | 17 | 30 | 17 |

Toilet facilities requirements for events where alcohol is available

|  |  |  |
| --- | --- | --- |
|  | Males | Females |
| Patrons | Toilet | Urinals | HandBasins | Toilet | HandBasins |
| <500 | 3 | 8 | 2 | 13 | 2 |
| <1000 | 5 | 10 | 4 | 16 | 4 |
| <2000 | 9 | 15 | 7 | 18 | 7 |
| <3000 | 10 | 20 | 14 | 22 | 14 |
| <5000 | 12 | 30 | 20 | 40 | 20 |

The above figures may be reduced for short events as follows:

|  |  |
| --- | --- |
| **Duration of event** | **Quantity required** |
| 8hrs plus | 100% |
| 6-8 hrs | 80% |
| 4-6 hrs | 75% |
| Less than 4 hrs | 70% |

The following should also be considered for existing or additional toilet facilities:

* Accessible toilets (this should be provided at an indoor and outdoor event. If not possible, people should be informed prior to the event so that a decision can be made to attend or not)
* Toilets should be located on flat ground and easily accessible
* Baby change facilities
* Cleaned and restocked regularly
* Located away from food, storage /service areas
* Weather protected
* Well-lit to not provide a security or safety risk
* Provide sharps disposal
* Provide soap and hand drying equipment

***In this section of your event plan state the number of toilets and accessible toilets that will be provided at your event and any additional facilities that you will be providing. Consider both permanent and temporary facilities. List the cleaning and inspection schedule that you will implement for your event. You must also display all types of toilets clearly on your site map.***

## Waste

### Waste Generation and Disposal

Incorporating the waste hierarchy for your event (see below) is a good way to reduce waste, especially landfill waste. It will make your event a more pleasant place to be and reduce your clean up time and costs.

### Waste Hierarchy

Most preferable

### Minimising Waste

One area likely to generate significant volumes of waste and litter at your event is single use food packaging and entertainment goods such as balloons, plastic bags, silly string and pamphlets. Avoiding these items where possible is a good place to start. This can be done by:

* Gain written commitment from stallholders (especially food vendors) to use recyclable packaging or other Waste Wise alternatives. If allowing use of compostable packaging, check with your service provider that they can be composted with your food collection service. Council’s organics processor doesn’t allow compostable packaging so recyclable packaging is the best alternative. Also, compostable packaging cannot go in the recycling bin so it’s best to avoid it unless high levels of patron education is planned.
* Check what materials are recyclable with the waste and recycling contractor for your event.
* Have a no plastic bag, polystyrene, balloon & straw policy (can provide paper straws if required for medical reasons)
* Consider if plastic water bottles are needed to be sold. Could a portable water station be set up instead?
* Partner with food recovery groups who will distribute food to those in need
* Encourage reusable alternatives by providing discounts for patrons who bring water bottles or keep cups and advertise to patrons.

### Reducing Litter

Avoiding disposable packaging items, will reduce the amount of litter and waste being produced and going to landfill. To further reduce waste and litter, you could:

* Ensure that bins are located together, ie. have general waste, recycling and food waste bins in ‘stations’ together. Try to have stations every 20m, this will reduce litter.
* Undertake a high level of patron education before and during the event to reduce packaging and increase recycling (e.g. performers, displays, placing a Waste Wise logo on promotional material)
* Provide glow-in-the-dark bin recycling signs if your event is at night
* Organise litter patrols during the event – a clean site is more likely to stay clean
* Reward vendors with waste wise practices and clean sites and create disincentives for vendors who have dumped rubbish at their site or in the incorrect bins.
* As bins are most likely to be contaminated during the ‘clean up’ at the end of an event, remove the bins before the clean-up and have volunteers sort the leftover waste at the end of the day.

### Waste Infrastructure

It is worth asking what sort of waste is likely to be generated by your stallholders and ensure ‘back of house’ waste systems for the most voluminous of that waste is provided. Food vendors, for instance, are likely to produce a lot of food and packaging waste. Consider:

* Are stallholders likely to dispose of lots of cardboard boxes, in which case it is best to order a cardboard recycling skip to avoid dumping or bins being clogged and unusable by patrons
* Another option for busy periods such as set up, lunch time and pack up is to ask volunteers to collect cardboard from stall holders
* Do coffee stalls need separate recycle bins for milk cartons or small compost collection bins for coffee grounds?

A clear indication of what goes in each bin will educate patrons and reduce the costs associated with having to tip contaminated recyclables into landfill. Sustainability Victoria has [downloadable bin signage](https://www.sustainability.vic.gov.au/Government/Signage-and-resources/Public-place-waste-signage) for all waste streams.

Coloured bin caps which sit on top of open bins (see picture below) make it easy for patrons to identify waste and recycling bins. The caps are usually covered with pictures indicating which items go into which bins.



 

## Water

Events must have a sufficient supply of freely available drinking water.

At outdoor events, organisers must:

* Provide one drinking fountain for every 200 patrons or part thereof. A washbasin does not constitute a drinking fountain or tap.
* Provide safe to drink water that is freely available
* Provide accessible pathways to water sources
* Provide signage to the water
* Consider layout carefully and avoid placing taps in areas that have the potential to create bottlenecks

Bottled drinking water is an unsustainable way of quenching thirst and another large generator of waste.

Consider hiring hydration stations and encourage patrons to bring their own non-disposable drinking bottles.

Please take into consideration if you are holding an outdoor event and you need to erect temporary structures or provide heavy vehicle access; know where the water pipes/mains are located. A burst water main is not ideal prior to or during an event and the event organiser will be liable for any associated costs. Be proactive and familiarise yourself with the event site. Council’s Community Events Officer can assist with providing this information and can be contacted on 9294 5722.

It should be noted for an indoor licensed venue, free or low cost water must be provided.

***In this section of your event plan it must clearly state how you will be providing adequate water for your event both temporary and permanent. Water points will also need to be clearly located on a site map that is available to the public and if all sites are not accessible the sites that are, need to be clearly marked.***

## Power

Power is often required to run an event. The options for power are either established mains power or temporary power i.e. generators. Some of Council’s parks and reserves have mains power; they include Ringwood Lake, Croydon Park and Jubilee Park. Please speak to Council’s Community Events Officer on 9294 5722 to find out more information. With the use of power for events comes an increase of risk and you will need to consider this when you are undertaking your Risk Management Plan. The following suggestions need to be taken into consideration to maintain a safe and successful event site.

Power considerations for all events (indoor and outdoor):

* Ensure you have a qualified electrician on stand by on the day of your event.
* Know your exact requirements for your event and the type of power that you will require i.e. 3-phase power, single-phase power.
* For an event with multiple power requirements, consider a contingency of providing 10% additional power resources to allow for incidentals.
* If site holders or external parties require power, ask them to nominate their requirements including what needs power and ensure that all electrical items at the event (including coffee machines, PA systems and rides) are tagged and tested. In your confirmation letter to site holders make it clear that they are only to power up what they have been given prior permission for and that all cords are in good functioning order and have been tagged and tested.
* Do not use power boards or double adaptors as you can overload the points depending on what is plugged in.
* All extension leads, appliances and anything to be powered must be tagged and tested by an accredited electrician.
* Don’t assume all power points are in working order. Test them prior to your event.
* Place the powered items in close proximity to the power source. Power leads are a trip hazard and need to be considered in your Risk Management Plan. Where possible all leads should be taped down or covered by cable matting. If this is not possible you need to place a barrier over the leads so that it is clearly not an access path.
* Do not join extension leads together to make a long lead as this can overload the cable and can cause fire hazards. Source the one lead for the required length.
* At any stage of your event, if you or event staff are not satisfied with the power set up, equipment or leads provided then you must act on it. As the event organiser you have the right to cut access to power based on the safety requirements of your event.

Power considerations for outdoor events:

* If you are using mains power either through an established power box or a pavilion you will need to seek permission from Sport and Recreation. All power boxes and pavilions are locked, and you will need to request keys from the Community Events Officer on 9294 5722. Please note that there may be a fee for usage.
* If you require generators use a reputable service provider.
* Prior to placing your order with the generator company know your power requirements. Make sure you discuss the requirement for leads, distribution boards and cable matting (to be placed over leads on the ground). Overestimate your requirements for cable matting.
* Under no circumstances are leads to be threaded through trees as this can cause fire hazards. Approved equipment for overhead leads needs to be supplied by the Generator Company and installed/set up by an accredited electrician.
* All electrical work is to be undertaken and checked by an accredited electrician.

Consider your programming in regard to your power requirements. Generators can be expensive and sometimes noisy to operate. For smaller events, question the value of the powered item as an enhancement to your program weighted against the additional planning and costs associated with your event.

Council recommends the use of solar or biodiesel fueled generators where possible to reduce the greenhouse gas emissions of the event.

***In this section of your event plan list the requirements for power and include a copy of a site map locating mains power and placement of generators.***

## Event Noise/Music

An outdoor entertainment event on public land must stay within the standard operating hours:

* Monday to Saturday – 7 am to 11 pm
* Sunday and public holidays – 9 am to 11 pm

You may require a permit for [**music noise**](https://www.epa.vic.gov.au/for-community/environmental-information/noise/music-noise/about-music-noise-from-venues-and-events) emitted from your:

* outdoor entertainment venue
* outdoor entertainment event

This applies to:

* businesses who want to hold public outdoor music events, like concerts
* people in the community who want to hold public outdoor events such as local community festivals, where music is part of the event.
* businesses and people in the community who want to extend an event or concert beyond the standard operating hours, or to operate more than six concerts in a financial year.

More information can be found in this link:

[Outdoor music noise and event permits | Environment Protection Authority Victoria (epa.vic.gov.au)](https://www.epa.vic.gov.au/for-community/environmental-information/noise/music-noise/outdoor-venue-noise-permits)

## Signage

Clear, prominent signage will add to the visitors’ level of enjoyment at an event. It can also reduce enquiries to staff in the information stand as signage can assist patrons in locating services and attractions.

It is worthwhile investing in corflute signs indicating where essentials such as toilets, drinking water and food areas are located and having stage program times. Signage font should be large and clear to read, contrasting colours and the use of universally recognised symbols are also effective.

If you would like to organise roadside promotional boards for your event, please refer to the below permit section.

***In this section of your event plan list all the signs and the location you intend to use at your event. Consider signs used as promotional material before the event and signs used during your event to direct people to a particular area or the location of a particular section of your event.***

## Smoking Laws

All events held on Council land are encouraged to be 100% smoke free. Free signage is available from DHHS through online order form: <https://www2.health.vic.gov.au/public-health/tobacco-reform>

The Tobacco Act 1987 prohibits smoking in the following areas**.**

**Under Age Events**

<https://www2.health.vic.gov.au/public-health/tobacco-reform/smoke-free-areas/under-age-events-smoke-free>

By law, smoking is prohibited at all public music or dance events that are organised for or predominantly attended by young people under the age of 18 years and at sporting venues during underage sporting events.

A guide and factsheet on smoke-free under-age events and ‘No smoking’ signs can be ordered without charge from the Resources and factsheets page.

**Food Fairs**

By law, smoking is prohibited:

* in all outdoor areas **at Food Fairs.** A food fair is an event where the principal activity is the supply of food for consumption at the event. Food Fairs must 100% smoke free.

A sign “***No Smoking – Food Fairs are Smoke Free****”* must be displayed at all entrances.

**Outdoor Dining Areas**

<https://www2.health.vic.gov.au/public-health/tobacco-reform/smoke-free-areas/outdoor-dining>

By law, smoking is prohibited:

* in outdoor areas at hospitality and food venues used for eating food. This includes footpath dining areas, courtyards and beer gardens during times food is being eaten, or is available to be eaten
* within 10 metres of a food stall or food vendor at organised outdoor event (other than a food fair).

A sign “***No Smoking with 10 metres of a Food Stall or Food Vendor****”* must be displayed at each stall/van/food vendor.

To complement smoke-free outdoor dining, smoking is banned in an outdoor drinking area if any part of that area is within 4 metres of an outdoor dining area, unless separated by a wall of at least 2.1 metres high. This means the two areas can be separated by either:

* a 4 metre buffer zone; or
* a wall of at least 2.1 metres high.

If the separation requirement is not met, smoking is banned in an outdoor drinking area. This law applies to the same venue as well as to neighbouring venues.

**Outdoor Drinking Areas**

<https://www2.health.vic.gov.au/public-health/tobacco-reform/smoke-free-areas/outdoor-drinking>

Smoking in outdoor drinking areas is banned when:

* an area has a roof in place, and
* the total actual area of wall surfaces exceeds 75 per cent of the total notional wall area.

Outdoor drinking areas include the following places if predominantly used for the consumption of drinks:

* a balcony or veranda
* a courtyard
* a rooftop
* a marquee
* a street or footpath
* any similar outdoor area.

Drinks can include both alcoholic and non-alcoholic drinks such as coffee.

**Children’s Recreation Areas**

Smoking is banned at and within 10 metres of outdoor public children’s playground equipment, skate parks and sporting venues during organised under-age sporting events, as well as in outdoor areas of public swimming pools.

## Transport, Parking, & Pedestrian Management

Events naturally necessitate the substantial movement of goods and people. The influx of freight and people to one centralised location presents event organisers with transportation conflicts that need to be managed.

Transport, movement and parking are important considerations in event site selection. Consider the following:

* The level of service provided by existing public transport services and active transport corridors.
* Interface between the public land and community facilities with the street network.
* Allocation of accessible parking (refer to the Accessibility Section)
* Be mindful of other activities that maybe occurring within or nearby your site that may also compete for parking, i.e. local games of sport.
* If parking is not sufficient at the site, you may need to provide parking areas away from the site and offer a shuttle service. If your event is in a high residential area and there is limited site parking available, you will need to put steps in place to manage the car parking in the residential streets.

 The event plan needs to consider these objectives:

* Safely separate event deliveries, patrons, participants and volunteers from traffic,
* Manage the reduced capacity of the road system,
* Manage the influx of demand on public transport, cycling and pedestrian pathways.
* Minimise the traffic and parking impact on the non‐event community and emergency services,
* Communications plan incorporates advertising of event’s transport and traffic aspects to advise of road changes and encourage participants to arrive by public and active transports.

A transport management plan details the transport and traffic requirements and controls. Should your event have any impact on traffic, parking or pedestrians a traffic management plan will need to be completed (by an appropriately qualified person). This may include traffic lane closure, a footpath closure or an influx of parking, all of which will need approval from Council’s Engineering department.

The table provides suggested strategies to manage the transport, movement and parking impacts for consideration in the traffic management plan.

|  |  |
| --- | --- |
| **Objectives**  | **Strategies**  |
| Separation of event deliveries, emergency vehicles and people.  | * All deliveries and unloading of goods and equipment needs to be conducted before the event opens to patrons
* Once the event begins, all delivery vehicles should be off site and access limited to emergency vehicles only
* Any vehicle movements within the event pedestrian zone during the event should be kept to a minimum, the speed limited to walking pace and whenever possible be escorted by event staff.
 |
| Manage the reduced capacity of the road system, | * Use signage to provide amply notification and alternative routes for traffic to reroute non event traffic.
 |
| Manage the influx of demand on public transport, cycling and pedestrian pathways.  | * If your event is likely to affect the operation of public transport services by causing an alteration in route, delay in services or requiring additional services, you must notify Public Transport Victoria.
* If you are planning a large event that will attract significant attendance it is recommended that you contact Public Transport Victoria to discuss the provision of extra public services on event day.
* Provide secure and safe bicycle parking facilities.
 |
| Minimise the traffic and parking impact on the non‐event community and emergency services. | * Offer parking at location independent from the event and provide a free shuttle bus to the venue.
* Remode patrons by encouraging them to take public or active transport.
* Investigate free shuttle bus options from key transport hubs such as Ringwood and Croydon stations. A local bus company may provide this as a free service in return for sponsorship opportunities.
 |
| Communications plan incorporates advertising of event’s transport and traffic aspects to advise of road changes and encourage participants to arrive by public and active transports.  | Actively promote the following: * Public transport routes to your event site.
* People to cycle to your event.
* Road closures and alternative detours.
* Alternative parking and shuttle services.
 |

***In this section of your Event Plan please state what arrangements you have in place for Traffic and Pedestrian Management including any road or footpath closures, car parking in residential areas and changes to public transport. Outline if you have organised any additional public transport options and link existing public transport options into your marketing strategy.***

## First Aid

The provision of First Aid facilities is essential to any event or festival and must be appropriately equipped and easy to find by patrons. The number of first aid posts and personnel required depends on the size of the event and the level of risk involved with the activities at the event. St John Ambulance has provided a guide based on the number of patrons, however as an event organiser you will need to assess the risk of the activities. If considerable risk activities are included as part of your event program, the emergency support services such as first aid providers should be included in the planning stages of your event and they can provide advice as to how many personnel and posts you may require.

St John Ambulance Australia has suggested the following as a general guide:

|  |  |  |
| --- | --- | --- |
| **Patrons** | **First Aiders** | **First Aid Posts \*** |
| 500 and under | 2 | 1 |
| 1,000 and under | 4 | 1 |
| 2,000 and under | 6 | 1 |
| 5,000 and under | 8 | 2 |
| 10,000 and under | 12 | 2 |
| 20,000 + | 22+ | 4 |

\* The number of First Aid posts required depends on what First Aid room facilities are available on site.

First Aiders should be trained by a certified agency to Level 2 competency as a minimum.

***In this section of your event plan state how many trained first aiders you will have on site, their name, contact details and the location they will be in at the event. First Aid posts should be clearly displayed on your site map and included in the staff briefing/induction process and incident must be recorded.***

## Security and Crowd Control

Event organisers are responsible for all security and crowd control aspects of their event. Based on the program (i.e. well-known artist or presenter), number of visitors/audience, the target audience and whether alcohol is available will determine if security is required. Choosing an appropriate security provider is essential to the success of an event and the safety of the public. Privately uniformed security must be licensed under the Private Agents Act 1966. It is also worth investigating whether the security providers have event and crowd control experience. You want to make sure that all security personal are trained to diffuse a situation as a first measure. If you are organising a major event, it is also useful to include the contracted security provider when planning the event from an emergency response point of view. A representative should attend a meeting with the event organiser, Police and emergency services who will be attending the event.

Developing a security plan and brief the security provider. Make sure evacuation routes/points, emergency response plans and a site map detailing first aid and Police points are included in the plan. Make sure all roles and responsibilities are clarified for the security providers to undertake their duties effectively. It should also be stressed that all security personal working your event must be briefed by their representative involved in the planning of your event before commencing their shift.

Keep in mind, if you are having temporary infrastructure such as staging or portable toilets security may be required for bump in and/or bump out to be sure they are not vandalised or stolen.

If you are organising a major event, the Victoria Police must be advised of your event and invited to be involved in the planning stages of your event. Contact numbers can be found at: https://www.police.vic.gov.au/events

For a guide on how many security officers you should have present at your event contact an accredited Security Company and ask for a quote based on your event specifics.

***In this section of your event plan please document what security and crowd control measures you will be using for your event. Clearly list the service provider, direct contact person, contact details, number of security staff, schedule and location during the event. If you have specific security/crowd control requirements due to the program schedule of your event, then you will also need to document this.***

## Weather

Extreme weather must be taken into consideration for both indoor and outdoor events when you are planning your event.

Extreme weather situations to consider include but are not limited to:

* Wet weather, thunder and electrical storms
* Extreme Heat
* High winds

Whilst you cannot plan or control the weather you can put steps in place in your planning process that will minimise risk and disruption to your event, event participants and staff. Keep an eye on the weather forecasts prior to your event through either news reports or the Bureau of Meteorology [www.bom.gov.au](http://www.bom.gov.au)

Here is a list of recommendations to include in your extreme weather plan:

* If your event is outdoors do you have a backup inside venue?
* Have you allowed extra time for your bump in if rain causes delays?
* Have you organised a communication plan should your event need to be cancelled?
* Have you provided sunscreen for staff and guests?
* Do you need to increase shaded areas to avoid sun, via bringing in additional marquees, umbrellas etc.?
* Do you need to implement shorter work shifts?
* When an electrical or thunder storm occurs how will you go about closing the event?
* In the case of storms and high winds how will you ensure your marquees are safely secured to avoid collapsing or being blown away?
* In the case of high winds what will you do to minimize the impact of closing all rides?

## Permits

This section includes information on a range of permits and approval processes related to organising events. Please note this is just a guide and other permits may apply.

### Liquor Licence

Having a wide range of food, drink and entertainment at an event will broaden its appeal to more members of the community.

The sale of alcohol at events that are primarily pitched towards families with young children is discouraged.

If you are selling or providing alcohol at an event you need to obtain the appropriate liquor licence. As the event organiser, you are responsible for the service of alcohol at your event - and for providing an environment where patrons and staff are safe and secure.

The Liquor Control Reform Act 1998 stipulates that anyone selling or serving liquor needs to obtain the correct licence. A liquor licence is required whenever alcohol is supplied, either directly or as part of an inclusive charge.

There are different types of licences required for certain types of events or selling arrangements.

* Temporary Limited Liquor Licence: Apply to the Victorian Commission for Gambling and Liquor Regulations (VCGLR)
* Major Events Licence: Apply to the Victorian Commission for Gambling and Liquor Regulations (VCGLR)

For advice on the correct type of liquor licence for your event please contact the Victorian Commission for Gambling and Liquor Regulation for more information <https://www.vcglr.vic.gov.au/liquor/major-or-temporary-event/apply-new-licence/licence-application-kits>

The process for obtaining a licence can take up to 8 weeks. You will need to develop an event/alcohol management plan to avoid the supply of alcohol to minors and ensure that the responsible service of alcohol must be in accordance with the Liquor Control Reform Act 1998. Contact the Victorian Commission for Gambling for further information about the Act on 1300 182 457.

If you decide to have alcohol at your event and are successful in obtaining a liquor licence you need to plan for the effects of alcohol consumption. These include:

* Extra toilets
* Additional First aid for injuries, intoxicated patrons and dehydration
* Security for disturbances caused by intoxicated patrons
* Location of alcohol service area/s on the site plan, including red line plan if appropriate
* Maximum number of people attending the event
* How you plan to control the serving of alcohol to people over the age of 18 years eg. x number of cans sold at any one time, cans must be opened
* Plans to ensure that patrons leave the venue in an orderly manner
* Times that alcohol will be served
* Type of drinking containers that the alcohol will be served in (suggest polycarbonate, cans or plastic and no glass)
* Types of alcohol available
* Types of non-alcoholic beverages available (encouraged) eg zero alcohol beer/cider, soft drink, coffee/tea, juice etc
* Free water must be available
* Anyone serving alcohol must be RSA trained (must have proof of RSA) display mandatory VCGLR signage

***In your event plan include a copy of the Liquor Licence Permit, proof of RSA and any additional resources you may require to hold a safe and responsible event.***

Council recommends you register your event with the Victoria Police Partysafe initiative <https://www.police.vic.gov.au/party-safe>

**Consumption of liquor or possession in unsealed container and behaviour near licensed premises**

A person must not, without a *Permit*, on a *Road*, any *Council**Land* or any open space to which the public have access:

consume or ingest any *Liquor*; or

have in his or her possession a bottle, can, wine cask or other receptacle, which contains *Liquor* and has been opened.

PENALTY: MAXIMUM TWENTY (20) PENALTY UNITS

*Clause* 0 does not apply:

to a person in licensed premises or authorised premises under the *Liquor Control Reform Act* 1998;

 or

where the consumption of *Liquor* is taking place at an organised function conducted with *Proper**Authority* or as part of a picnic with family and/or friends within a *Municipal Reserve*, provided that no nuisance is caused to other persons in the area and the persons concerned leave the area in a clean and tidy condition afterwards.

For further information please contact Council’s Local Laws Department on 9294 5607.

### Provision of Food and/or Temporary Food Event Permit

Please see the above Provision of Food (3.10) for details on food and/or temporary food event permits.

### APRA & PPCA Event Licence

Entertainers at any event or festival performing songs that are not their own original songs must obtain a permit from OneMusic prior to the event.

If you're using recorded music or music videos to enhance your event in any way, then you will most likely need a licence and permission from the copyright holder to do so.

Examples of such uses include:

* Playing protected recorded music in public
* Screening music videos in public
* Playing protected recorded music and/or radio to your phone customers on hold
* Broadcasting recorded music over the radio or TV
* Broadcasting music videos on TV

For further information visit the OneMusic website for details.

<https://onemusic.com.au/media/Information-Sheets/Events.pdf>

Licensing Enquiries: 1300 62 162

Email: events@onemusic.com.au

Website: onemusic.com.au

Allow one month for this process and make sure you adjust your budget accordingly as a permit fee will apply.

***In your event plan include a copy of the APRA and/or PPCA Permit and clearly identify the entertainers and/or recorded music that the permits apply to.***

### Roadside Promotional Boards Permit

Approval is required from Council to erect signage for promotional purposes around the municipality on any Council owned land. An application can be downloaded from Council’s website, using this link [Community Billboard Application Form](https://www.maroondah.vic.gov.au/Customer-service/Forms-and-permits/Forms-and-Permits/Community-advertising-billboards-on-Council-land-application-form)

If you wish to erect promotional signs on private property (residential or business) you will need to seek the permission of the landowner. You must also check that you comply with the Planning Scheme for Maroondah. Clause 52.05 addresses advertising and has specific requirements if you want to place boards on privately owned land. The following addresses the size and duration requirements:

* A sign with an advertisement area not exceeding 5 square metres publicising a local educational, cultural, political, religious, social or recreational event not held for commercial purposes. Only one sign may be displayed on the land, it must not be an animated or internally illuminated sign and it must not be displayed longer than 14 days after the event is held or 3 months from its creation, whichever is sooner. A sign publicising a local political event may include information about a candidate for an election.
* A sign publicising a special event on the land or in the building on which it is displayed, provided no more than 8 signs are displayed in a calendar year and the total number of days the signs are displayed does not exceed 28 in that calendar year. The sign must be removed when the event is finished.

***In this section of your event plan include a copy of the Roadside Promotional Boards Permit and clearly identify the timeframe and locations of the boards.***

### Temporary Banning of Dogs, Alcohol and other items

In order to hold an event in a safe and responsible environment it may be necessary to apply for a temporary ban of dogs, alcohol and other items.

Council owned land may already have particular bans in place and it is worth checking this prior to confirming your arrangements.

Contact Local Laws on 9294 5607 to discuss your specific event requirements that may affect any standing local laws in place and/or temporary measures you may require. If you are specifically changing a local law on a temporary basis you will need to go through an approval process that will require the support of Council’s Local Laws and Governance.

### Fireworks/Pyrotechnics Displays

If you are planning on having fireworks/pyrotechnic displays at your event you must contact Council’s Community Events Officer on 9294 5722.

### Road and Footpath Closure Permits

If you are planning on closing any road or footpath approval is required from Council’s engineering department.

Traffic Management Plans including any road, footpath or carpark closure require approval from Council’s Engineering department.

The following items are required when applying for a Road and/or Footpath Closure Permit:

* Current Public Liability Insurance
* Traffic Management Plan (incorporating a risk assessment)
* Written notification to affected businesses/residents/public transport providers if applicable
* Notification to Emergency Services of possible detours or expected significant delays.

For more information on Council’s permit applications visit [Road and Footpath Closure Permits](https://www.maroondah.vic.gov.au/Development/Roads-footpaths-and-drains/Roads-and-footpaths/Road-and-footpath-closure-permits) or contact Council’s Engineering and Building Services team on 9298 4327.

***In this section of your event plan, list what permits you require to hold your event. You will need to document the process and consider what needs to be included in your marketing strategy.***

### Infrastructure and Temporary Structures

Some events will require an Occupancy Permit for Places of Public Entertainment (POPE) and Siting Consent for Temporary Structures.

**Occupancy Permit for Places of Public Entertainment (POPE)**

In some instances, events require a POPE Occupancy Permit when any building or place is used for an event which would not normally be used for that purpose.

If the event is held by a Non for profit or gain *Community Based Organisation* (eg: local sports clubs) a POPE Occupancy permit is only required when:

* the number of persons in the place at any one time during the event or activity exceeds 5,000

For all other events an application for a POPE Occupancy Permit is required if it meets any of the following:

* The event site area is larger than 500m²
* It is conducted in an enclosed or semi enclosed area
* Entry to and from the event is controlled
* Admission can be gained by payment of a fee. A fee includes donations and gifts.

Examples of such events include football finals and grand finals run by the competition’s association, open air concerts, markets, carnivals, festivals and agricultural shows. A POPE occupancy permit is required for these events irrespective of whether they are conducted by a community- based organisation or a commercial business.

**Siting Consent - Temporary Structures**

Siting Consent is required for all temporary structures that have an Occupancy Permit issued by the Victorian Building Authority and the activities are held within those structures. This applies to:

* tents, marquees or booths with a floor area greater than 100m²
* seating stands for more than 20 persons
* stages or platforms (including sky borders and stage wings) exceeding 150m² in floor area
* prefabricated buildings exceeding 100m² other than ones placed directly on the ground

Examples of such consents consent are Circus tents, seating stands for football finals, stages for musical events.

For further information on a POPE or Siting Consent please contact Council’s Municipal Building Surveyor on 9298 4327.

## COVIDSafe Events - Victorian Government Requirements

Event organisers must make sure that their event operates in accordance with the current Victorian Government requirements for public events.

More information can be found here: [Events in Victoria | Coronavirus Victoria](https://www.coronavirus.vic.gov.au/public-events-in-Victoria)

## Event Planning Template

The below template is to help ensure you have covered all areas required for your event plan and clearly identify who is responsible:

|  |  |
| --- | --- |
| **Name of event:** |  |
| **Date of event:** |  |
| **Location of event:** |  |
| **Time of event:** |  |
| **Event coordinator:** |  |
| **Target audience:** |  |
| **Objectives of event:** |  |
| **Detailed description of event:** |  |
| Event Planning | PersonResponsible | Action | Date to be completed |
| **Read Council’s Events Policy**[Events held on Council Land Policy](https://www.maroondah.vic.gov.au/About-Council/Our-organisation/Policies/Events-held-on-Council-Land-Policy) |  |  |  |
| **Submit Event Application Form** [Running an event on Council Land Application Form](https://www.maroondah.vic.gov.au/Customer-service/Forms-and-permits/Forms-and-Permits/Running-an-event-on-Council-land-application-forms) |  |  |  |
| **Catering**Apply for any required food permits Requirements - power etc. |  |  |  |
| **Permits**Apply for any permits:Liquor LicenceFoodTraderRoad ClosureRoadside Advertising BoardFireworks or Pyrotechnics displayCOVIDSafe Event Approval |  |  |  |
| **Prepare Budget** Establish budget sourceSource sponsorshipDetermine other sources of income ie. site fees etc.Did you allow for GST? |  |  |  |
| **Venue**Ensure venue is bookedConfirm accessible accessConfirm access times |  |  |  |
| **Protocols**Are you inviting Mayor or Councillors?Are you inviting other special guests?Protocol regarding state and federal funding.Any other funding requirements? |  |  |  |
| **Develop Event Program**Book performers, entertainers and Master of CeremoniesSend confirmations and pay deposits |  |  |  |
| **Design traffic management plan including:** SignageDisabled parkingVIP parkingPedestrian accessEmergency vehicle accessEntry and exit pointsLighting Apply for road closures (if required)Alternative transport - look at transportation options including parking |  |  |  |
| **Risk Management**Conduct Risk AssessmentCreate Risk Management PlanDevelop Contingency Plans (wet weather)Notify Police and Fire Brigade if necessary |  |  |  |
| **Emergency Management** Identify emergency access pointsIdentify Emergency Coordination CentreIdentify Evacuation locationsNotify emergency servicesWill emergency services be on site?Type of crowd control to be usedFirefighting equipment identifiedSafety Officers |  |  |  |
| **Infrastructure**Book all equipment -stage, lighting, PA system etc.Book infrastructure - marquees, chairs etc.Book portable toilets if required |  |  |  |
| **Insurance**Do you have P/L insurance? Minimum $20,000,000.00 requiredObtain all relevant insurance information from contractors ie. rides, performers etc. |  |  |  |
| **Book vendors and confirm in writing:** Times of operationRequest details of electrical equipmentRequest copy of Certificate of Currency (insurance)Copy of approval from Streetrader |  |  |  |
| **Security**Security bookedSecurity briefedTwo-way radios booked (if required) |  |  |  |
| **First Aid**Emergency support services or Level 2 qualified first aiders at a minimum |  |  |  |
| **Advertising**Press, radio, tv, social media, roadside boards etc.Add event to “What’s on in Maroondah” [What's on in Maroondah Event Calendar](https://www.maroondah.vic.gov.au/Explore/Whats-on-in-Maroondah/Events-calendar) |  |  |  |
| **Design plan of venue/event site including:** StagesToiletsFoodFirst aidStall holdersParkingEmergency AccessEntry/Exit pointsFixed Structures |  |  |  |
| **Water**What access is there to water on site?Do you need additional requirements? |  |  |  |
| **Staffing**What are your minimum requirements?Do you need volunteers? |  |  |  |
| **Waste Management**Audit bins on site and order more if requiredSweep of venue before eventRubbish management during eventCleaning of venue after event |  |  |  |
| **Develop timetables/running sheets/speeches**Program finalisedRunning sheet writtenRunning sheet given to MC etc.Speeches written |  |  |  |
| **Bumping out**Staff and volunteers are debriefed and signed offContractors are off siteEnsure all equipment is collected ie. witches’ hats, bollards, radios etc.All infrastructure is packed away and removed from siteAll rubbish is removedVenue is secureComplete any incident reporting |  |  |  |
| **After the event**Committee DebriefEvaluate the eventSuggestions for improvementSend out thankyou’s |  |  |  |

# RISK MANAGEMENT PLAN AND EMERGENCY RESPONSE PLAN

## Risk Management Plan

To help achieve a successful and safe event, spending time completing a thorough risk assessment will be a key planning tool in your event management preparation. Applying a systematic approach to this task will order your thinking, to ensure that unwanted risks are identified, and controls are put in place to reduce or mitigate the risks. As the event organiser you have a duty of care for the safety of everyone involved.

The best time to commence this process is in your concept stage. You may start with identifying the event location, financial support, people, resources and other fundamental elements to demonstrate how to achieve the key event objective. As you progress through to the planning stage you will be engaging with a number of stakeholders and with their input, you will be able to map out operational risk detail.

The completed Risk Management Plan will require submission to the authorising Council Events Officer, as part of the application process. Each event has unique attributes and considerations, requiring an individual effort to the development of a risk assessment. Large events will demand a greater level of rigour to the Risk Management Plan. i.e. engagement of an independent Event Safety Officer etc. In these instances, Council will work with the event organiser to provide specific instruction and guidance.

## What is Risk?

“Risk is the chance of something happening that will have an impact upon objectives”

## What is Risk Management?

It is the systematic application of a process to step you though the planning and delivering your event, to achieve the great success you and the public expect.

## Risk Management Process

Examples of Unwanted Risks that impede a successful event.

* Insufficient funding
* Lack of volunteers in event organising or on the day
* Advertising (late, not targeted etc) does not generate enough interest
* Size of venue/location too small for event
* Volunteers not inducted and do their own thing
* Loss of crowd control
* Food poisoning
* Dangerous temporary structures
* Serious incident

Benefits of good Risk Management

* High quality and successful event
* Patron satisfaction and heightened community wellbeing
* Demonstrates planning competence
* Attracts funding
* Satisfies regulatory compliance (ie.WorkSafe, Food Act)
* Ensures emergency management planning
* Identified roles and responsibilities
* Mitigation of incidents
* A safe event for patrons
* Positive public image

## How to Conduct a Risk Assessment

1. Consider the risk context, nature, potential consequences and the likelihood to determine the level of risk.
2. Brainstorm, use resources, discuss with others to consider, recognize and describe risks for the entire event.
3. What can be done to eliminate the risk or put in place actions to reduce the risk to an acceptable level
4. Requires ongoing checking and supervising to ensure treatment solutions are working and responding to change

The following pages provide the necessary tools to step you through the Risk Assessment process. Considerable attention will need to be given to “treating” the risk. That is working out what can be done to eliminate or reduce it to an acceptable level of low or medium risk rating.

### Risk Analysis - Step 1 Consequences

The *consequence* if an event happens can range from **5** to **1**. ‘Consequence’ refers to the outcome or impact of an event.

|  |  |  |
| --- | --- | --- |
|  | **Consequence** |  |
| **5** | Catastrophic | Multiple fatalities, national or international media attention, event cancelled, long term reputational damage, potential class action |
| **4** | Major | Major injury/ies requiring hospitalisation, single fatality, reported in national media, major impact to event, reputational damage, litigation involving court action |
| **3** | Moderate | Major injury or multiple minor injuries from one incident requiring medical treatment by doctor, reported in Melbourne media, disruption to event, legal issues/litigation |
| **2** | Minor | Injury requiring first aid or medical treatment, breaches of regulation, local media, criticism but no permanent damage |
| **1** | Insignificant | Minor injury, no negative media attention, non-compliance, issues resolved within normal event management process. |

### Risk Analysis - Step 2 Likelihood

The *likelihood* of an event happening can range from **A** to **E**. ‘Likelihood’ is a general description of probability or frequency. Choose

|  |  |  |
| --- | --- | --- |
|  |  |  |
| **A** | Certain | The event is expected to occur in most circumstances |
| **B** | Likely | The event will probably occur in most circumstances  |
| **C** | Possible | The event should occur at some time  |
| **D** | Unlikely | The event could occur at some time |
| **E** | Rare | The event may occur only in exceptional circumstances |

### Risk Analysis - Step 3 Risk Matrix

The aim of risk analysis is to assess the likelihood of it occurring and the consequences should it happen. Combining these two provides a **Risk Rating**.

|  |  |  |
| --- | --- | --- |
|  | **Risk Matrix** |  |
| **Likelihood** | **Consequence** |
| **1INSIGNIFICANT** | **2MINOR** | **3MODERATE** | **4MAJOR** | **5CATASTROPHIC** |
| **ACERTAIN** | **High** | **High** | **Extreme** | **Extreme** | **Extreme** |
| **BLIKELY** | Medium | Medium | **High** | **Extreme** | **Extreme** |
| **CPOSSIBLE** | Low | Medium | **High** | **Extreme** | **Extreme** |
| **DUNLIKELY** | Low | Low | Medium | **High** | **Extreme** |
| **ERARE** | Low | Low | Medium | **High** | **High** |

* Broken glass on site
* Syringes on site
* Cracked paths that may cause tripping hazards
* Blocked paths
* Water leaks

### Risk Examples

* Staff are overworked
* Staff are dehydrated
* Staff are unsure of roles
* Staff are unsure of correct ways to use equipment
* Adverse social media publicity
* Contractor or supplier ethical performance
* Corporate social responsibility
* Customer service protocols
* External communications & marketing
* Issues and grievances
* Organisational code of conduct
* Privacy of guests
* Uninvited guests attend
* Overcrowded in car park
* Contractor’s safety processes are missing steps
* Extreme Heat
* Rain
* Strong Winds
* Staff safety
* Guest Safety
* Contractor Safety
* Volunteer Safety

|  |  |  |  |
| --- | --- | --- | --- |
| **Location of Event:** | **Name of Event:** | **Description of Event:** | **Date:** |
| **Date of Event:** | **Name of Event Organiser:** | **Risk Assessment Completed by:** |
| **Hazard** | **Risks** | **Existing Risk Controls** | **Risk****Rating** | **Additional Mitigation Strategies** | **Responsibility to Monitor** |
| **Insufficient Funding** | Reduction of size of event.Attraction to event affected.Negative public image. | Introduced budget controls and tracking that highlights exacts targets at each week. Budgeted for less funds received than predicted to allow for shortfall. | C2Medium | Began sponsorship proposals much earlier than previous years to ensure funds are secured. |  |
| **Lack of Volunteers on the day** | Insufficient information, assistance and direction to event patrons and stallholders.Breakdown of incident response process. | Allocate 3 additional volunteers to act as floaters on the day and cover any additional or unfilled roles.  | C3High | Began the volunteer recruitment earlier. Held volunteer meetings.Send confirmation 1 week out from the event. |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

## Emergency Response Plan

An Emergency Response Plan outlines how you will respond to an emergency at your event.

The Emergency Response Plan should clearly identify one key person (the Warden) who is responsible for managing emergencies at your event. The Warden’s contact details should be given to all of those who may be involved in emergency response at your event (for example security and first aid).

Examples of possible inclusions for your Emergency Response Plan include:

* A site plan with Melways references, identifying both access (for emergency services) and evacuation routes. Your site plan should also show the location of First Aid
* A clear outline of roles – who is responsible for decision making? Who is in charge of notifying Emergency Services?
* An evacuation procedure – where will you exit from? Where will you go to? How will you communicate this with your guests (signage, announcements)?
* An assessment of the kind of emergencies that may occur? For example fire, vehicle accident or stage collapse. Then look at their likelihood and how you can reduce this risk
* A clear procedure for dealing with lost children. Who is in charge of minding the child and what steps will you put in place to resolve the situation? Where can lost children be found? How will parents know what to do when they cannot find their child?
* An emergency communications plan – always dial 000 first, who will report and log the incident, who else needs to be contacted (family?) and how will you communicate with your guests?

Copies of your Emergency Response Plan should be given to all staff, volunteers and contractors that will be on your event site.

**If warranted the Municipal Emergency Management Plan will override your Emergency Response Plan.**